## Sheet1
Issues found during testing UI Package V1.1.11 // SGLT1- EasyTouch
No. | Issue | Description | Desired Solution | Attachments | Responsible
1 | Lagging | The screen transitions are somewhat slow. It takes about a second to switch to cook mode, but returning to the home screen is quick and seamless. | Have the same response time as the home button on all menu. | IMG_5304 | Elreha | Elreha to investigate ( Dina)
2 | Heating cycle doesn’t stops | When the temperature and time are set in cook mode, the pan temperature should stay at the set temperature for the specified time. However, currently, even after reaching the target temperature, the heating continues throughout the cycle, causing the pan temperature to rise much higher than the set temperature. | The heating cycle should be maintained on the set temperature during the entire time cycle by cycling the unit ON/OFF | IMG_5303 | Mohsen | Mohsen to look into Hysteresis
3 | Heating doesn’t stops when pressing stop | After heating up the unit and pressing stop, the heating does not turn off until we press the home button and return to the main menu. | heating cycle should shut off when pressed stop | IMG_5296 | Sales | To be changed on Storyboard. (Confirm with John L.)
4 | Heating Cycle works only once | The unit only operates during the first cycle after being turned on. It fails to work on the second cycle, requiring us to shut off the unit and turn it back on to get it functioning again. | Should be performing the heating cycle everytime. |  | Elreha/ Mohsen | Dina to verify, and Mohsen to look into it from I/O Board
5 | Timer doesn’t pauses | When the cooking process is paused and then resumed, the timer should continue from where it paused. However, it currently continues to count in the background, and when resumed, it starts from the elapsed time. | The timer should pause and resume back at same time. | IMG_5301 | Elreha | Covered in Pt. 3
6 | Editing a step is not possible after start | Once we set a temperature and time and start cooking, pressing stop to adjust the settings is not possible. The UI doesn't allow readjustments after the start button is pressed, requiring the user to redo the entire process. | User should be able to edit time and temperature. | IMG_5290 | Elreha | Covered in Pt. 3 | .
7 | Fonts on Message Step too small | When we add a meesage step on the unit, the font size is very small. | The font should be as big as the "Add Ingredient" fonts in the start. | IMG_5291 | Elreha | Elreha to fix it
8 | Saving a recipe | If you want to save a modified version of an existing recipe, you go through the same process as saving it for the first time. This includes editing the recipe name, choosing a picture. | For user friendly experience, we should be not going through all this step on a saved recipe. A saved recipe should just have modification like cooking step, time, temperature. |  | Elreha / Sales | Have it because to use it as a template. To confirm it with John L.
9 | Doesn’t shows the set product temperature | When cooking on product probe mode, the pan doesn’t shows the set product temperature on display, rather it shows the set Pan temperature. | Should show both Pan and Product Temperature, or product temperature (Live) when on product probe mode | IMG_5305 | Elreha/ Sales | Elreha suggestion: add another step after product probe mode which would ask if the user wants to continue in product mode and then all we can set is the time and the unit cooks on product probe temperature for the input time.

## Sheet2
Issues found during testing UI Package V1.2.0
No. | Issue | Description | Desired Solution | Attachments | Responsible
1 | Orientation was changed | The screen displays in the Landscape mode | Need to show in Portrait mode | UI V1.2.0 package release on 03.03.2025\IMG_8368.jpeg | Fixed
2 | Enter icon hides due to the landscape orientation | After inputing the set points, the values cannot be entered by pressing check mark icon. It is hidden due to the small screen in landscape mode. | If the screen is in Portrait mode, this migt be solved. | UI V1.2.0 package release on 03.03.2025\IMG_8369.jpeg | Fixed
3 | 5 minutes for Uploading .tar package | After Flashing the UI with MFG Tools, and the usb stick was inserted with latest .tar package. It took around 5 minutes for the display to show its updated. | Might require lesser time to do this job |  | Observation
Issues found during testing UI Package V1.2.1
No. | Issue | Description | Desired Solution | Attachments | Responsible
1 | Hysteresis and offset option | No Hysteresis and offset option for temperature profile testing. | Add Hysteresis and offset |  | Fixed- new tempertures range with Elreha
2 | Sounds | No options for selecting different sounds. | Add sound options for us to test and pick the best one |  | Fixed
3 | Preheat complete | Once set temperature is met, shows "Preheat complete" - Not fit to the screen | "Preheat complete" fit within the page |  | Fixed
Issues found during testing UI Package V1.2.2
No. | Issue | Description | Desired Solution | Attachments | Responsible
1 | Hysteresis and offset option | Adjust Hysteresis and offset | Adjust Hysteresis and offset |  | temperature range ±100°F Cleveland Request
2 | Sounds | No options for selecting different sounds. | Add sound options for us to test and pick the best one |  | Elreha.
3 | Sounds | Speaker does not sound when calls for alarms/notification. Speaker does sound when moving the slider for max and min volume. | call for sounds when notify or functional operation. |  | Elreha
Issues found during testing UI Package V1.2.3 dated 04.04.2025
No. | Issue | Description | Desired Solution | Attachments | Responsible | Items for next release (04-10-2025)
1 | Hysteresis option | Adjust Hysteresis | Adjust Hysteresis range from 0 to 5. | #VALUE! | Elreha. Cleveland Request
2 | Product probe Hysteresis option | No option for Product Probe Hysteresis | Add Product Probe Hysteresis |  | Elreha.
3 | Product Probe PID options | No options for Product probe cooking | Add the options for product probe cooking too |  | Elreha. Critical
4 | Sounds | No options for turning off the sound. | Add sound options like "no sound" to turn off the sound |  | Elreha.
5 | Sounds | No sound for message step displayed | Add sound for message step displayed |  | Elreha.
6 | sound menu | configures the sound menu to relative model. | shouldn’t see water fill for SGLT1 |  | Elreha.
7 | Heater error | "E101:Heater error" message pops up freaquently without any reason | No action required, as this was tested with V1.2.3 and next release should resolve this. |  | Observation.
8 | Pan not down | When pan down limit switch is made to disengage manualy during cooking time count down, the timer doesn't stops and proceed to complete the process. In addition, the pan not down error is displayed only once when cooking started and does not showup again if the pan is not nown for the second or third time. | During Heating cycle, Tilting icons should greyout (not let the user to tilt.) | videos EasyTouch package from Elreha\pan not down when disengagged manually-cooking timer doesn't stop.MOV | Observation
9 | Pan not down | When pan down limit switch is not activated the process continues and there is no disruptions until completion. |  | videos EasyTouch package from Elreha\pan not down when disengagged manually-error is not popped up for the 2nd time.MOV
10 | Pan not down | When pan is up the cooking timer count down pauses. When pan is back to its original position the timer resets and starts counting from beginning. | Timer should stop when tilted and resume countdown when upstraight. | videos EasyTouch package from Elreha\13. Pan not down.MOV | Elreha Critical | Items for next release (04-10-2025)
11 | Live errors (Active Errors) | Add live error list | If Errors cleared by UI, and still exists should show in the live error list. |  | Elreha. Cleveland Request. Phase 4
12 | Bootloader: Not checking .inf file everytime during initiallization process | Expected: If a new IO board with " .hex" file is connected to UI, it should check and compare ".inf" file in the IO board with the one in its own memory. If it not matches then it should upload ".bin " file to the IO board. Happening: Once the unit is turned ON, the UI sends command to stop bootloading mode and begin its run mode. It is not checking whether the IO board has a firmware in its memory. | The UI should check the IO board firmware everytime during the startup. If there is no firmware, UI should upload ".bin" file which is already in its memory.
13 | Bootloader: Should display message if ".bin" file is missing in its memory | UI should hold ".bin" file for all the model numbers. At present we cannot verify it. | Should display a message if the UI is missing the firmware for specific units and recommends user to update it
14 | Bootloader: IO Firmware Updater: Display exact message for denoting firmware file compatibility | Steps followed: USB stick inserted in no tagged slot--> Service --> update firmware -->Select Firmware file --> .bin file After pressing tick mark at the bottom, a message displayed "Firmware file not Compatible" | The displayed message should be specific, why it is not compatible | videos EasyTouch package from Elreha\12. IO firmware updater.MOV
15 | Bootloader: IO board compatibility issue | If the UI is connected to a IO board with different which is not related to model number in UI , then it displays message like "IO boaard not compatible". We cannot know which firmware is already in the IO board | Should display exact message with the firmare details.
16 | Bootloader: Not compatibility issue | when IO board with SGL T1 is connected to UI with selecting model No SGL T5. It accepts the firmware. This looks not good. | Need to look into it. | videos EasyTouch package from Elreha\14. Not compatibility issue.MOV
17 | Communication error | When this error pops up, it is stopping the heating process | Should be resolved with the next release. | #VALUE!
18 | stopped accepting Input once pressed cleared in timer | If we pressed clock option and entered a wrong time and when trying to re-enter the time using clear option, we cannot enter it. | Should be resolved | L:\Engineering\Priv\Test Registry Documents\Tests\Test no 000241 - Testing the EasyTouch Package released by Elreha\videos EasyTouch package from Elreha\stopped accepting Input once pressed cleared in timer.MOV
Note on E37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Verified by doing the following process: 1. Erasing the new IO board and fixing it in the unit 2. Connecting the UI to IO board 3. Pressing the power button ON and waiting for UI initialization. 4. Observed the IO board changes from bootloader mode to run mode. 5. There were no functions found operational in the unit
Note on E38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Since UI should upload “.Bin” every time if “.inf” file mismatches or its missing. At present there is no display screen for verifying this.