## Sheet1
Issues found during testing UI Package V1.1.14 // SGLT1- EasyTouch
| No. | Issue | Description | Desired Solution | Attachments | Responsible
| 1 | Lagging | The screen transitions are little slow. It is better than before but needs to have smooth transitiion b/w screens | Have the same response time as the home button on all menu.
11/12/2024 | 2 | "E101: Heater error" pops up | In the middle of heating cycle, "E101: Heater error" pops up with a check mark. It does not harms or stops the heating but the error stays on the screen until acknowledged by clicking on the check mark. | To not have this error popped randomly until otherwise there is an actual problem. |  | Elreha/ Mohsen | Criteria for heater error? Mohsen to check into the time lapse for this error. Measuring the slope/ condition when the error occurs. Elreha to check one minute timer is reset.?
11/12/2024 | 3 | Tilting Jog | Once the tilt up/down button is pressed and released, the motor stops after few ms | To have the motor stop immediately when the button is released. The issue was fixed in the previous 2 updates but it showed up back |  | Elreha
11/14/2024 | 4 | Pan tilted without any command. | The pan tilted in the middle of operation without user giving any command. The Pan did not stopped on limit switch and triggered the motor reset switch. | I/O firmware issue. Firmware to be fixed. |  | Mohsen | Mohsen updated the firmware on 11/18/2024. Unit to be tested further
| 5 | Adding Offset and Hysteresis in Configuration. | Ability to add/modify hysteresis and offset from UI | Added Register 4 and 7 |  | Elreha
Total 200 events and 100 error logs